## Sheet1
S.NO | NAME | ROLE | RESPONSIBILITIES | REMARKS
1 | Ravi Sai Chowdary Akkina | Test Lead | Test planning, guidance, Monitoring and test control
2 | Ravi Sai Chowdary Akkina | Tester | Test data collection, Generating test scenarios
3 | Ravi Sai Chowdary Akkina | Tester | Test case documentation, test execution, defect reporting and tracking for admin module
4 | Ravi Sai Chowdary Akkina | Tester | Test case documentation, test execution, defect reporting and tracking for Personal banking module
5 | Ravi Sai Chowdary Akkina | Tester | Test case documentation, test execution, defect reporting and tracking for corporate banking module

## Sheet2
SNO | TASK | DAYS | DURATION | REMARKS
1 | Understanding and Analyzing requirements | 2 | 4-12-2023 to 9-12-2023
2 | Review meeting | 1 | 2023-12-10
3 | Generating Test scenarios | 2 | 11-12-2023 to 12-12-2023
4 | Reviews | 2 | 13-12-2023 to 14-12-2023
5 | Test case Documentation | 1 | 2023-12-15
6 | Reviews | 1 | 2023-12-16
7 | Test data collection | 1 | 2023-12-17
8 | Reviews | 1 | 2023-12-17
9 | Verifying Test Environment Setup | 1 | 2023-12-18
10 | Create Test Batches | 1 | 2023-12-19
11 | Sanity Testing | 1 | 2023-12-19
12 | Comprehensive testing | 1 | 2023-12-20
13 | Sanity Testing | 1 | 2023-12-20
14 | Selecting Test Cases | 1 | 2023-12-20
15 | Regressing Testing | 2 | 21-12-2023 to 22-12-2023
16 | Sanity Testing | 1 | 2023-12-23
17 | Selecting Test Cases | 1 | 2023-12-24
18 | Regression Testing cycle -2 | 2 | 25-12-2023 to 26-12-2023
28 | Final Regression | 1 | 2023-12-26
29 | Evaluating Exit Criteria | 1 | 2023-12-27
30 | Collecting all artifacts | 1 | 2023-12-27
31 | Test Summary Report | 1 | 2023-12-28